## Gantt Chart Template
PREDECESSOR TASK - - T1.2 T1.2 T1.2 T1.5 T1.6 T1.8
|  | PROJECT TITLE | Wild Type vs Mutant: understanding hereditary lysozyme amyloidosis | [7 empty] | COMPANY NAME | [8 empty] | UPC
|  | PROJECT MEMBERS | Juan David Ricaurte, Junwei Lin, Abril Cesar, Marina Cabredo | [7 empty] | DATE | [8 empty] | 15.09.2026
WP | TASK ID | TASK TITLE | TASK OWNER | PLANNED START DATE | PLANNED END DATE | DURATION (days) | REAL DURATION | OUTPUT | PREDECESSOR TASK | Definition of done | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5
[11 empty] | M | T | W | TH | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
WP1 – Project Setup & Planning
| T1.1 | Create the Gantt Chart Template | Juan David | 2026-09-15 | 2026-09-15 | 1 | 15 sep-15 sep | Gantt chart template (.xlsx) | - | .xlsx document created with a templete of a general Gantt Chart.
| T1.2 | Initialize GitHub repository | Junwei Lin | 2026-09-17 | 2026-09-17 | 1 | 17 sep-17 sep | GitHub repository shared with all members | - | Repo created and shared with the members
| T1.3 | Repository structure | Abril | 2026-09-17 | 2026-09-17 | 1 | 17 sep-17 sep | Repository folder structure with .gitignore, README and report files | T1.2 | Creation of the Gantt, Status and Figures folders in the github repository. Creation of gitignore, readme and report documents.
| T1.4 | Edit report document | Abril | 2026-09-17 | 2026-09-17 | 1 | 17 sep-17 sep | Report template following the journal format | T1.2 | The report document have the structure of the general format recommended of a magazine
| T1.5 | Write readme document | Junwei Lin | 2026-09-17 | 2026-09-17 | 1 | 17 sep-17 sep | README document | T1.2 | The document explain what our project is about, why is important to research it and what questions are we gonna answer.
| T1.7 | Define roles | All | 2026-10-01 | 2026-10-01 | 1 | 02 oct- 02 oct | Role assignment table | T1.6 | Each member is clear about their role in the project
| T1.8 | Complete the Gantt chart & risk matrix | Juan David & Abril | 2026-10-01 | 2026-10-08 | 1 |  | Completed Gantt chart and risk analysis | T1.7 | Gantt chart + risk analysis committed to repo.
| M1 | MILESTONE: Roles & planning approved | — | — | — | — | — | — | — | All members are agree whit scope & plan
WP2 – Study the dessease and proteine
| T2.1 | Research papers about the desease | All | 2026-10-01 | 2026-10-04 | 4 | 1 oct- 5 oct | Reference list with short notes on the selected papers (max. 3) | T1.7 | The group have recolected as maximum 3 papers that allows to understand what is the disesasse about
| T2.2 | Define analysis folders | Junwei Lin | 2026-10-02 | 2026-10-02 | 1 |  | Documented Git workflow and analysis folder structure | T2.1 | Rules for branches written in the README; folders data/, gene/, protein/, structure/, species/ created.
| M2 | MILESTONE: Disease understood & workflow ready | — | — | — | — | — | — | — | Papers read and folders created in repo
WP3 – Gene level analysis
| T3.1 | Validate CDS files and translate to protein | Juan David | 2026-10-09 | 2026-10-12 | 2 |  | Validation note on WT and mutant CDS files | T2.1 | WT and mutant CDS start with ATG, end with a stop codon and their translation matches the protein FASTA.
| T3.2 | Align CDS WT vs mutant and locate the mutation | Juan David | 2026-10-13 | 2026-10-13 | 1 |  | CDS alignment file and mutation table | T3.1 | Position, codon change and mutation type identified.
| T3.3 | Summarize gene-level results (figure + summary) | Juan David | 2026-10-14 | 2026-10-14 | 1 |  | Gene-level figure and summary text | T3.2 | Alignment figure and short summary committed to gene/ in the repo.
WP4 – Protein level analysis
| T4.1 | Align WT vs mutant protein and confirm the amino-acid change | Junwei Lin | 2026-10-09 | 2026-10-12 | 2 |  | Protein alignment with confirmed amino-acid change | T2.1 | Amino-acid change match the gene-level result of T3.2.
| T4.2 | Compare physicochemical properties and domains | Junwei Lin | 2026-10-13 | 2026-10-13 | 1 |  | Table of physicochemical properties and domains | T4.1 | Table with MW, pI, GRAVY, instability and domains (UniProt/InterPro) for WT and mutant.
| T4.3 | Summarize protein-level results | Junwei Lin | 2026-10-14 | 2026-10-14 | 1 |  | Protein-level figure and summary text | T4.2 | Figure and short summary committed to protein/ in the repo.
| M3 | MILESTONE: Sequence-level analyses done | — | — | — | — | — | — | — | Gene and protein results committed and consistent with each other
WP5 – Structure analysis
| T5.1 | Search PDB for WT and mutant structures | Marina | 2026-10-09 | 2026-10-12 | 2 |  | List of selected structure IDs | T2.1 | Structures chosen and IDs documented
| T5.2 | Obtain the mutant structure | Marina | 2026-10-13 | 2026-10-13 | 1 |  | Mutant structure file | T5.1 | Mutant structure saved in structure/ with a basic quality check.
| T5.3 | Superimpose WT vs mutant and measure differences | Marina | 2026-10-14 | 2026-10-14 | 1 |  | Superposition image and with local changes | T5.2 | Report the local changes with around the mutation.
| T5.4 | Structural figures and summary | Marina | 2026-10-15 | 2026-10-15 | 1 |  | Structural figures and summary text | T5.3 | Figures and short summary committed to structure/ in the repo.
WP6 – Cross-species comparison
| T6.1 | Select third species and validate orthologs | Abril | 2026-10-09 | 2026-10-12 | 2 |  | Selected species and validated ortholog list | T2.1 | Third species chosen; orthologs confirmed for human, C. l. familiaris and the third species.
| T6.2 | Build ortholog FASTA and run multiple alignment | Abril | 2026-10-13 | 2026-10-13 | 1 |  | Ortholog FASTA file and multiple alignment | T6.1 | Single FASTA with the three proteins and alignment file committed to species/.
| T6.3 | Check conservation of the mutated position and summarize | Abril | 2026-10-14 | 2026-10-14 | 1 |  | Conservation figure and summary text | T6.2 | Conservation of the mutated position described, with a figure and short summary in species/.
| M4 | MILESTONE: Structure & cross-species analyses done | — | — | — | — | — | — | — | Structure and species results committed to repo
WP7 – Biological integration
| T7.1 | Check numbering and results are consistent across levels | Abril | 2026-10-15 | 2026-10-15 | 1 |  | Consistency checklist (mutation name and numbering) | T6.3 | Same mutation name, position and numbering in all analyses; contradictions listed and resolved.
| T7.2 | Build causal chain, answer the two research questions and write the discussion | Abril | 2026-10-15 | 2026-10-15 | 1 |  | Discussion section and summary figure | T7.1 | Discussion section and summary figure committed to report/; both research questions answered explicitly.
| M5 | MILESTONE: Integration & report draft complete | — | — | — | — | — | — | — | Discussion written and all sections present in the report
WP8 – Report & final submission
| T8.1 | Write each member's results section in the report | All | 2026-10-16 | 2026-10-19 | 2 |  | Results sections drafted in the report | T7.2 | Gene, protein, structure and species sections written in the report by their owners.
| T8.2 | Edit report and figures (style, numbering, references) | Marina | 2026-10-16 | 2026-10-19 | 2 |  | Edited report with unified style, captions and references | T8.1 | Unified style, numbered figures with captions and complete references.
| T8.3 | Final repository check and submission | Junwei Lin | 2026-10-19 | 2026-10-20 | 2 |  | Final repository version submitted on main | T8.2 | README updated, repo reproducible and clean, final version on main and submitted.
| M6 | MILESTONE: Final submission | — | — | — | — | — | — | — | Repository submitted
Formulas:
DURATION (days) = NETWORKDAYS([PLANNED START DATE],[PLANNED END DATE])